## Sheet1
#	Date	Section	Features	Attributes	Priority	Progress	added by	Reviews
		General	Client Server approach	Multiple Servers and Clients	1
			Developer	Owner equivalent rights except changing existing sales	2
			Multiple Stock house and shops at every location		2
			One user one branch - Manager Updates user branch		1
			encryption		2
			license		2
			show branch name while logging in for User		3
			user access and new branches addition		3
			Deployment to single shop or so, radio button		2
			shop requests store for stock and similarly store request for new procurement		3

		Billing	Total Price and Qty		1	done
			Do not accept item for billing when not in shop		1	done
			Item Qty editable	>1 entry exists (0 or less implies removal)	1	done
			Display	Item total price, GST per item,	1	done
			expiry, change in inventory only after billing complete	Separate entry for same item if 2 exp dates	1	awaiting decision
			press "enter" for next item		2	done

									Priority	Proposed Completion Date
									1	26/may/2020

		Total Sales	List of bills	Bill Id, Customer name, Date Time, total price, total Qty, Item	1	done
			Search (Multiple Column search)	all columns	2	done
			Date Range	List ,Total value,	2	done
			Click on particular Bill	Display bill	1	done
			Modify Bill (Money based Exchange)	expiry date check and 15 days from billing date for exchange	2
			user can see his own shop sales		1	done

		Update Inventory	Only user assigned to the shop can update		1	done
			Shop and Stock house		1	done
			Gst and expiry update		1	done
			data import	through csv, pdf, .db file (structured), unstructured.	2
			delete row completely when qty 0		0	done

		Search Inventory	Search (mulitple column)	area, branch, item, barcode, expiry date, shop,stock house	2	done
			All users can search all.		1	done

		Branch	Modify Branch		1	done
		User	modify User		1	done